## in
plan | plan-event | document-url | date | predicted-date | name | notes
King's Lynn and West Norfolk Local Plan 2044 | publish-notice-intention-commence |  |  | 30th June 2026 | King's Lynn and West Norfolk Local Plan 2044 | Publishing the notice of intention to commence Local Plan preparation is a new requirement. It gives communities and stakeholders advance notice of plan?making and sets out when and how they can get involved. The notice must be published at least 4 months before Gateway 1.
King's Lynn and West Norfolk Local Plan 2044 | scoping-consultation-start |  |  | 1st September 2026 | King's Lynn and West Norfolk Local Plan 2044 | This is a new requirement and seeks to ask what people would like to see in their Local Plan and how they want to be engaged in the process.
King's Lynn and West Norfolk Local Plan 2044 | scoping-consultation-end |  |  | 29th September 2026 | King's Lynn and West Norfolk Local Plan 2044 | All comments (representations) on the scoping consultation must be received on or before this date.
King's Lynn and West Norfolk Local Plan 2044 | sites-consultation-start |  | 2nd February 2026 |  | King's Lynn and West Norfolk Local Plan 2044 | An opportunity for residents, town and parish councils, councillors and stakeholders to comment on sites submitted through our call for sites. This is not a formal consultation required by legislation.
King's Lynn and West Norfolk Local Plan 2044 | sites-consultation-end |  | 31st May 2026 |  | King's Lynn and West Norfolk Local Plan 2044 | All comments on the submitted sites must be received on or before this date.
King's Lynn and West Norfolk Local Plan 2044 | gateway-1-self-assessment |  |  | 30th October 2026 | King's Lynn and West Norfolk Local Plan 2044 | This new requirement is a self assessment summary confirming that we have published the timetable and notice, completed the scoping consultation, and have a project plan in place to begin the formal stage of preparing the Local Plan. Once we complete Gateway 1, we have 30 months to prepare and adopt the plan.
King's Lynn and West Norfolk Local Plan 2044 | plan-content-evidence-consultation-start |  |  | 1st April 2027 | King's Lynn and West Norfolk Local Plan 2044 | This second formal consultation sets out the proposed vision, aims and objectives, and a summary of the policy topics the plan will cover. We will also publish a summary of the evidence proposed to support the plan. This stage should include propsoed site allocations.
King's Lynn and West Norfolk Local Plan 2044 | plan-content-evidence-consultation-end |  |  | 16th May 2027 | King's Lynn and West Norfolk Local Plan 2044 | All comments (representations) on the proposed Local Plan content and evidence consultation must be received on or before this date.
King's Lynn and West Norfolk Local Plan 2044 | gateway-2-advice-sought |  |  | 1stNovember 2027 | King's Lynn and West Norfolk Local Plan 2044 | This new requirement is a formal method of obtaining feedback from a planning inspector on the draft plan and supporting evidence, ensuring our approach aligns with national policy, guidance and legislation.
King's Lynn and West Norfolk Local Plan 2044 | gateway-2-advice-published |  |  | 30th December 2027 | King's Lynn and West Norfolk Local Plan 2044 | Date of publication will depend on the duration of Gateway 2.
King's Lynn and West Norfolk Local Plan 2044 | proposed-plan-consultation-start |  |  | 1st April 2028 | King's Lynn and West Norfolk Local Plan 2044 | This 6 week consultation is on the final version of the plan and includes the proposed site allocations.
King's Lynn and West Norfolk Local Plan 2044 | proposed-plan-consultation-end |  |  | 16th May 2028 | King's Lynn and West Norfolk Local Plan 2044 | All comments (representations) on the proposed Local Plan consultation must be received on or before this date.
King's Lynn and West Norfolk Local Plan 2044 | gateway-3-advice-sought |  |  | 1st September 2028 | King's Lynn and West Norfolk Local Plan 2044 | This new requirement is a final check by an external assessor to confirm the plan meets planning regulations and the tests of soundness, before formally submitting it for Examination.
King's Lynn and West Norfolk Local Plan 2044 | gateway-3-advice-published |  |  | 30th October 2028 | King's Lynn and West Norfolk Local Plan 2044 | Date of publication will depend on the duration of Gateway 3.
King's Lynn and West Norfolk Local Plan 2044 | examination-submitted |  |  | 15th November 2028 | King's Lynn and West Norfolk Local Plan 2044 | The proposed Local Plan must be submitted for an independent Examination carried out by a Planning Inspector. The Examination should last no longer than 6 months.
King's Lynn and West Norfolk Local Plan 2044 | examination-recommendations-published |  |  | 28th February 2029 | King's Lynn and West Norfolk Local Plan 2044 | Date of publication will depend on the duration of the Examination.
King's Lynn and West Norfolk Local Plan 2044 | main-modification-consultation-start |  |  | 1st Match 2029 | King's Lynn and West Norfolk Local Plan 2044 | Main modifications consultation dates will depend on the duration of the Examination.
King's Lynn and West Norfolk Local Plan 2044 | main-modification-consultation-end |  |  | 15th April 2029 | King's Lynn and West Norfolk Local Plan 2044 | Main modifications consultation dates will depend on the duration of the Examination.
King's Lynn and West Norfolk Local Plan 2044 | adopted |  |  | 31st May 2029 | King's Lynn and West Norfolk Local Plan 2044 | Consideration of adopting the proposed Local Plan as the development plan for the Borough